## march_2017
ID | Task | Description | Status | Tracking
1 | Routing Algorithms | Read and comprehend routing algorithms | done
2 | Create Ns3 MAC | Create a MAC module copying the Adhoc and validate funcitonality, also can do the same inheriting from adHoc | done | - 2017-March-17: Done and Documented at Github Wiki Link Below: https://github.com/balart40/big_data_iteso_phd_public/wiki/NS3_with_MANET#creating-a-new-wifi-mac-model
3 | Know how MAC runs | Research how does MAC run continuously, check wave | on progress | - 2017-March-21: Review Adhoc Class, Aodv and Wave Modules - Reviewed AODV, uses neighbor class from NetWorkLayer through InternetStack class through routing which uses the neighbor class
4 | MAC modified | Modify MAC to print Tx and Rx packets | pending
5 | ESSOA NS3 Draft | Create UML of ESSOA class on NS3 | pending
6 | Implement ESSOA | Implement ESSOA with the Nodes weight only the cardinality | pending
7 | Validate ESSOA | Validate ESSOA | pending
8 | Energy Models | integrate energy models To ESSOA MAC | pending
9 | Validate EM | validate energy models | pending
10 | metrics | perform metrics | pending
11 | ESSOA enhanced | enhance ESSOA with new findings and improvements | pending
12 | Compare ESSOA | perform comparisons | pending
13 | start Article | start article draft | pending
14 | Routing Algorithms | start with routing algorithms | pending