## march_2017
ID | Task | Description | Status | Tracking | Date
∞ | Routing Algorithms | Read and comprehend routing algorithms papers exposing the advantages and disadvantages of the research found | on progress | - Next Meeting: Thursday 7 of abril of 2017 - Present AODV (OLSR, DSDV if possible) - Papers to review: - 2012_a_survey_of_energy_aware_routing_and_mac_protocols_in_manets_trends_and_challenges - 2016_Power-efficient routing schemes for MANETs a survey and open issues - 2017_march_A_Comprehensive_Classification_of_MANETs_Routing_Protocols | jueves-7-abril-2017
2 | Create Ns3 MAC | Create a MAC module copying the Adhoc and validate funcitonality, also can do the same inheriting from adHoc | done | - 2017-March-17: Done and Documented at Github Wiki Link Below: https://github.com/balart40/big_data_iteso_phd_public/wiki/NS3_with_MANET#creating-a-new-wifi-mac-model | viernes-17-marzo-2017
3 | Know how MAC runs | Research how does MAC run continuously, check wave | on progress | - 2017-March-21: Review Adhoc Class, Aodv and Wave Modules - Reviewed AODV, uses neighbor class from NetWorkLayer through InternetStack class through routing which uses the neighbor class | jueves-7-abril-2017
4 | MAC modified | Modify MAC to print Tx and Rx packets | done | - 2017-March-30: Reviewed Prints of MAC class functions with and without traffic | Jueves-30-marzo-2017
| Neighbor Discovery on New Mac | Implement the neighbor discovery in the new MAC class | on progress |  | Jueves-30-marzo-2017
5 | ESSOA NS3 Draft | Create UML of ESSOA class on NS3 | pending |  | viernes-14-abril-2017
6 | Implement ESSOA | Implement ESSOA with the Nodes weight only the cardinality | pending |  | viernes-21-abril-2017
7 | Validate ESSOA | Validate ESSOA | pending |  | viernes-28-abril-2017
8 | Energy Models | integrate energy models To ESSOA MAC | done | -2017-March-21: Talked with NetAnim Mantainer and applied temporal fix/patch to test | Done
9 | Validate EM | validate energy models | done | -2017-March-21: Validated energy models, net anim energy graphic now working | Done
10 | metrics | perform metrics | pending |  | viernes-5-mayo-2017
11 | ESSOA enhanced | enhance ESSOA with new findings and improvements | pending |  | viernes-12-mayo-2017
12 | Compare ESSOA | perform comparisons | pending |  | viernes-19-mayo-2017
13 | start Article | start article draft | pending |  | viernes-2-junio-2017
14 | Routing Algorithms | start with routing algorithms | pending |  | viernes-9-junio-2017